## Roadmap
The Firm - Roadmap
2022 - Annual Review
| Priority | Category | Initiative | Details | Implementation Timeframe | Complexity (High, Med, Low) | Budget
[7 empty] | One Time |  | Recurring
[7 empty] | Hardware/ Software Costs | Implementation Costs | Monthly Fees | Annual Fees
x |  | Business - Finance | New Accounting System | The Firm is currently assessing new accounting platforms. Goal will be to move physical system to the cloud. Firm has outgrown current system. | 2022 Q1 & Q2 | High | TBD | TBD | TBD | TBD
x |  | Security | Multi-Factor Authentication | Multi-Factor Authentication (MFA) has become a standard security control for remote user authentication. Firm needs this in place. | 2022 Q1 | Low | TBD | 20000 | TBD | TBD
x |  | Technology & Security | Backup and Disaster Recovery | Current back up device will be end of life in March 2022. Move to cloud and right size if need be. | 2022 Q1 | Low | 10000 | 5000 | 2000 | 24000
x |  | Business | Document Management Deployment | The Firm would like to review and evaluate various document management systems. Goal will be to migrate to a cloud system by end of year. | 2022 Q4 | High | TBD | 70000 | TBD | TBD
|  | Technology & Security | Switch Refresh | Replacement of core and access switching needed due to expansion of staff. | 2022 Q2 & Q3 | Medium | 40000 | 15000 | 500 | 6000
|  | Technology & Security | Firewall Replacement/Upgrade | The Firm's current firewalls will be end of life in June 2022 | 2022 Q2 & Q3 | Medium | 8000 | 10000 | 0 | 2000
|  | Technology & Security | Backup and Disaster Recovery testing | Simulated outage to confirm back up and disaster recovery proceedure works. Time objectives and available data meets expectations. | 2022 Q3 | Medium | 0 | 4400 | 0 | 0
x |  | Technology | Fleet Refresh | Need to develop plan for future fleet refreshes. Goal will be to move away from workstations and general to standardization. (30% of inventory will be replaced) | 2022 Q3 | Medium | 40000 | 25000 | 0 | 0
x |  | Business - Office Consolidation | Office Downsizing | The Firm will be decreasing office space. Coordination and reorganization of all office technology will be needed. | 2023 Q1 | Medium | TBD | TBD | 0 | 0
x |  | Technology | Server/SAN Replacement | On premise host servers and storage will be end of usable life December 2022. Plan will need to be determined and put in place early 2023. | 2023 Q1 | High | 75000 | 35000 | 0 | 5000
| KEY: | [5 empty] | HW/SW | Prof Srv | Per Month | Per Year
| High priority. To be addressed as soon as possible. | [5 empty] | 173000 | 184400 | 2500 | 37000
Medium priority. To be address within 3-6 months.
Low priority. To be addressed within 9+ months.
Completed initiative.
The above information is based on estimates for budgetary needs.